# ServiceNow Event-Driven Integration - One Page Roadmap

## Project Overview

Integration of JIRA, GitHub, Ansible Automation Platform, and Azure Red Hat OpenShift with ServiceNow using event-driven architecture for automated ticket and change request creation.

________________________________________________________________________________

## Phase 1: Tool Analysis & Process Review (3 Weeks)

### Objective

Analyze existing processes and event management capabilities for each tool.

| Tool | Duration | Key Activities | Deliverables |
| --- | --- | --- | --- |
| **JIRA** | 3 days | • Review current issue management processes<br>• Analyze webhook configurations<br>• Document event types and triggers<br>• Map current alerting mechanisms | • JIRA Process Analysis Document<br>• Event Mapping Matrix<br>• Integration Requirements |
| **GitHub** | 3 days | • Review repository workflows<br>• Analyze CI/CD pipeline events<br>• Document security alert processes<br>• Map deployment workflows | • GitHub Process Analysis Document<br>• Workflow Event Catalog<br>• Integration Requirements |
| **Ansible** | 3 days | • Review automation job processes<br>• Analyze job execution workflows<br>• Document failure handling procedures<br>• Map notification mechanisms | • Ansible Process Analysis Document<br>• Job Event Catalog<br>• Integration Requirements |
| **OpenShift** | 3 days | • Review cluster monitoring processes<br>• Analyze Prometheus alerting<br>• Document pod/deployment workflows<br>• Map incident response procedures | • OpenShift Process Analysis Document<br>• Alert Catalog<br>• Integration Requirements |

Total Duration: 12 business days (~3 weeks)

________________________________________________________________________________

## Phase 2: Architecture Design & Approval (4 Weeks)

### Objective

Design event-driven architecture and obtain stakeholder approval.

| Week | Activities | Deliverables |
| --- | --- | --- |
| **Week 1** | • Design event hub architecture<br>• Create decision maps<br>• Document integration patterns<br>• Define event flow diagrams | • Architecture Design Document<br>• Decision Maps<br>• Event Flow Diagrams |
| **Week 2** | • Review with technical team<br>• Refine architecture based on feedback<br>• Create technology stack recommendations<br>• Document security considerations | • Revised Architecture Document<br>• Technology Stack Decision<br>• Security Architecture |
| **Week 3** | • Present to stakeholders<br>• Address questions and concerns<br>• Update architecture as needed<br>• Prepare approval documentation | • Stakeholder Presentation<br>• Updated Architecture<br>• Approval Package |
| **Week 4** | • Finalize architecture<br>• Obtain formal approvals<br>• Document approved design<br>• Prepare for implementation | • Approved Architecture Document<br>• Sign-off from stakeholders<br>• Implementation Readiness Checklist |

Total Duration: 4 weeks

Key Decision Points:

Event management platform selection (Kafka/RabbitMQ/Event Hubs)

ServiceNow integration approach

Event processing architecture

Security and compliance requirements

________________________________________________________________________________

## Phase 3: Tool Integration (24 Weeks)

### Objective

Integrate each tool with ServiceNow event-driven architecture.

| Tool | Duration | Key Activities | Deliverables |
| --- | --- | --- | --- |
| **JIRA Integration** | 6 weeks | • Configure JIRA webhooks<br>• Implement event ingestion<br>• Create ServiceNow mapping<br>• Test end-to-end flow<br>• Implement acknowledgment<br>• User acceptance testing | • JIRA Integration Complete<br>• Test Results<br>• Documentation<br>• UAT Sign-off |
| **GitHub Integration** | 6 weeks | • Configure GitHub webhooks<br>• Implement HMAC verification<br>• Create event processing logic<br>• Map to ServiceNow tables<br>• Test workflows<br>• User acceptance testing | • GitHub Integration Complete<br>• Test Results<br>• Documentation<br>• UAT Sign-off |
| **Ansible Integration** | 6 weeks | • Configure Ansible webhooks<br>• Implement job event processing<br>• Create deployment mappings<br>• Test automation flows<br>• Implement status updates<br>• User acceptance testing | • Ansible Integration Complete<br>• Test Results<br>• Documentation<br>• UAT Sign-off |
| **OpenShift Integration** | 6 weeks | • Configure Prometheus Alertmanager<br>• Implement Kubernetes event processing<br>• Create pod/deployment mappings<br>• Test high-volume scenarios<br>• Implement filtering logic<br>• User acceptance testing | • OpenShift Integration Complete<br>• Test Results<br>• Documentation<br>• UAT Sign-off |

Total Duration: 24 weeks (~6 months)

Integration Activities (per tool):

Week 1-2: Webhook configuration and event ingestion

Week 3-4: Event processing and ServiceNow mapping

Week 5: Testing and refinement

Week 6: User acceptance testing and documentation

________________________________________________________________________________

## Timeline Summary

| Phase | Duration | Start | End |
| --- | --- | --- | --- |
| **Phase 1: Tool Analysis** | 3 weeks | Week 1 | Week 3 |
| **Phase 2: Architecture & Approval** | 4 weeks | Week 4 | Week 7 |
| **Phase 3: JIRA Integration** | 6 weeks | Week 8 | Week 13 |
| **Phase 3: GitHub Integration** | 6 weeks | Week 14 | Week 19 |
| **Phase 3: Ansible Integration** | 6 weeks | Week 20 | Week 25 |
| **Phase 3: OpenShift Integration** | 6 weeks | Week 26 | Week 31 |

Total Project Duration: 31 weeks (~7.75 months)

________________________________________________________________________________

## Key Milestones

| Milestone | Target Week | Description |
| --- | --- | --- |
| **M1: Analysis Complete** | Week 3 | All tool analyses completed and documented |
| **M2: Architecture Approved** | Week 7 | Event hub architecture design approved by stakeholders |
| **M3: JIRA Live** | Week 13 | JIRA integration deployed to production |
| **M4: GitHub Live** | Week 19 | GitHub integration deployed to production |
| **M5: Ansible Live** | Week 25 | Ansible integration deployed to production |
| **M6: OpenShift Live** | Week 31 | OpenShift integration deployed to production |

________________________________________________________________________________

## Resource Requirements

| Role | Allocation | Key Responsibilities |
| --- | --- | --- |
| **Project Manager** | 100% | Project coordination, stakeholder management, timeline tracking |
| **Solution Architect** | 75% | Architecture design, technical decisions, approval process |
| **ServiceNow Developer** | 100% | ServiceNow integration, API development, record creation |
| **Backend Developer** | 100% | Event processing, tool integrations, webhook development |
| **DevOps Engineer** | 50% | Infrastructure setup, deployment, monitoring |
| **QA Engineer** | 75% | Testing, test automation, UAT coordination |
| **Business Analyst** | 50% | Process analysis, requirements, UAT support |

________________________________________________________________________________

## Success Criteria

✅ All 4 tools analyzed and processes documented

✅ Event hub architecture designed and approved

✅ All 4 tools integrated with ServiceNow

✅ Automated ticket creation operational for all tools

✅ Acknowledgment mechanism working for all integrations

✅ User acceptance testing passed for all integrations

✅ Production deployment completed for all tools

________________________________________________________________________________

## Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Architecture approval delays | High | Early stakeholder engagement, clear decision maps |
| Tool integration complexity | Medium | Phased approach, proof of concept for each tool |
| Resource availability | Medium | Early resource planning, backup resources identified |
| ServiceNow API limitations | Medium | Early API testing, workaround strategies prepared |

________________________________________________________________________________

## Next Steps

**Immediate:** Begin Phase 1 - JIRA process analysis

**Week 1:** Schedule stakeholder meetings for architecture review

**Week 3:** Prepare architecture design documents

**Week 4:** Begin architecture approval process

________________________________________________________________________________

Document Version: 1.0

Last Updated: [Current Date]

Status: Draft - Pending Approval