# Implementation Roadmap

## ServiceNow Event-Driven Integration Project

## Document Information

**Document Type:** Implementation Roadmap

**Project:** ServiceNow Event-Driven Integration

**Version:** 1.0

**Date:** [Current Date]

**Author:** [Author Name]

**Status:** Draft - Pending Approval

________________________________________________________________________________

## 1. Executive Summary

This roadmap outlines the step-by-step implementation plan for integrating JIRA, GitHub, Ansible Automation Platform, and Azure Red Hat OpenShift with ServiceNow using an event-driven architecture. The implementation is divided into phases with clear deliverables, timelines, and dependencies.

### 1.1 Project Phases Overview

| Phase | Name | Duration | Key Deliverables |
| --- | --- | --- | --- |
| Phase 0 | Planning & Setup | 2-3 weeks | Project plan, infrastructure setup |
| Phase 1 | Foundation & Event Management | 4-6 weeks | Event management layer, basic processing |
| Phase 2 | ServiceNow Integration | 3-4 weeks | ServiceNow API integration, record creation |
| Phase 3 | Tool Integrations | 6-8 weeks | JIRA, GitHub, Ansible, OpenShift integrations |
| Phase 4 | Resilience & Reliability | 2-3 weeks | Queue management, retry logic, outage handling |
| Phase 5 | Acknowledgment & Feedback | 2-3 weeks | Acknowledgment mechanism, source system updates |
| Phase 6 | Testing & Optimization | 3-4 weeks | End-to-end testing, performance tuning |
| Phase 7 | Production Deployment | 2-3 weeks | Production rollout, monitoring, documentation |

Total Estimated Duration: 24-34 weeks (6-8.5 months)

________________________________________________________________________________

## 2. Phase 0: Planning & Setup

### 2.1 Objectives

Establish project foundation

Set up development infrastructure

Define detailed requirements

Create project governance structure

### 2.2 Tasks and Deliverables

#### Week 1: Project Kickoff

Tasks:

[ ] Conduct project kickoff meeting with stakeholders

[ ] Define project scope and objectives

[ ] Identify and assign project team members

[ ] Establish communication channels and meeting cadence

[ ] Create project repository and documentation structure

Deliverables:

Project charter document

Team roster and RACI matrix

Communication plan

Project repository setup

Dependencies: None

________________________________________________________________________________

#### Week 2: Infrastructure Planning

Tasks:

[ ] Evaluate and select event management platform (Kafka/RabbitMQ/Event Hubs)

[ ] Design infrastructure architecture

[ ] Plan network and security requirements

[ ] Identify ServiceNow instance details and access requirements

[ ] Create infrastructure provisioning plan

Deliverables:

Infrastructure architecture diagram

Technology stack decision document

Network and security design

Infrastructure provisioning scripts/templates

Dependencies: Phase 0, Week 1

________________________________________________________________________________

#### Week 3: Requirements Refinement

Tasks:

[ ] Review and refine tool analysis document

[ ] Define detailed event-to-ticket mapping rules

[ ] Document ServiceNow table structures and fields

[ ] Define priority and categorization rules

[ ] Create data mapping specifications

Deliverables:

Detailed requirements document

Event-to-ticket mapping matrix

ServiceNow data model document

Field mapping specifications

Dependencies: Phase 0, Week 1-2

________________________________________________________________________________

### 2.3 Success Criteria

[ ] All stakeholders aligned on project scope

[ ] Infrastructure plan approved

[ ] Requirements documented and approved

[ ] Development environment ready

### 2.4 Risks and Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Unclear requirements | High | Conduct detailed requirements workshops |
| Infrastructure delays | Medium | Start infrastructure setup early |
| Resource availability | Medium | Secure resources early, plan for contingencies |

________________________________________________________________________________

## 3. Phase 1: Foundation & Event Management

### 3.1 Objectives

Set up event management infrastructure

Implement event ingestion layer

Create event normalization and validation

Establish monitoring and logging

### 3.2 Tasks and Deliverables

#### Week 1-2: Infrastructure Setup

Tasks:

[ ] Provision event management platform (Kafka/RabbitMQ)

[ ] Configure Kafka clusters (3+ brokers)

[ ] Set up topic structure (critical, high, standard queues)

[ ] Configure replication and partitioning

[ ] Set up monitoring for event platform

[ ] Implement backup and disaster recovery

Deliverables:

Event management platform deployed

Topic configuration documented

Monitoring dashboards created

Backup procedures documented

Dependencies: Phase 0 completion

________________________________________________________________________________

#### Week 3-4: Event Ingestion Service

Tasks:

[ ] Develop webhook receiver service

[ ] Implement webhook endpoints for each tool

[ ] Create event validation logic

[ ] Implement event normalization

[ ] Add rate limiting and throttling

[ ] Implement authentication/authorization

[ ] Create event schema registry

Deliverables:

Webhook receiver service deployed

Event validation framework

Event normalization service

API documentation

Dependencies: Phase 1, Week 1-2

________________________________________________________________________________

#### Week 5-6: Event Queue Management

Tasks:

[ ] Implement event queuing logic

[ ] Create priority-based queue routing

[ ] Implement queue monitoring

[ ] Set up dead letter queue handling

[ ] Create queue management APIs

[ ] Implement queue capacity alerts

Deliverables:

Queue management system

Queue monitoring dashboards

Dead letter queue handler

Queue management documentation

Dependencies: Phase 1, Week 3-4

________________________________________________________________________________

### 3.3 Success Criteria

[ ] Events can be ingested from test sources

[ ] Events are normalized and validated

[ ] Events are queued correctly by priority

[ ] Monitoring and alerting functional

[ ] Dead letter queue operational

### 3.4 Testing

[ ] Unit tests for event ingestion

[ ] Integration tests for queue management

[ ] Load tests for event ingestion capacity

[ ] Failover tests for event platform

________________________________________________________________________________

## 4. Phase 2: ServiceNow Integration

### 4.1 Objectives

Integrate with ServiceNow REST API

Implement record creation logic

Create change request and incident creation

Implement field mapping and transformation

### 4.2 Tasks and Deliverables

#### Week 1: ServiceNow API Setup

Tasks:

[ ] Obtain ServiceNow instance access

[ ] Create service account with appropriate roles

[ ] Set up OAuth 2.0 authentication

[ ] Test ServiceNow API connectivity

[ ] Document ServiceNow API endpoints

[ ] Create ServiceNow API client library

Deliverables:

ServiceNow API client

Authentication mechanism

API connectivity verified

ServiceNow API documentation

Dependencies: Phase 1 completion

________________________________________________________________________________

#### Week 2: Record Creation Logic

Tasks:

[ ] Implement change request creation

[ ] Implement incident creation

[ ] Create field mapping logic

[ ] Implement data transformation

[ ] Add data validation

[ ] Handle ServiceNow API errors

[ ] Implement response parsing

Deliverables:

Record creation service

Field mapping configuration

Data transformation logic

Error handling framework

Dependencies: Phase 2, Week 1

________________________________________________________________________________

#### Week 3: Routing and Categorization

Tasks:

[ ] Implement event-to-table routing logic

[ ] Create priority mapping rules

[ ] Implement category assignment

[ ] Add assignment rules

[ ] Implement SLA calculation

[ ] Create routing configuration

Deliverables:

Routing engine

Priority mapping rules

Category assignment logic

Routing configuration

Dependencies: Phase 2, Week 2

________________________________________________________________________________

#### Week 4: Testing and Refinement

Tasks:

[ ] Test change request creation

[ ] Test incident creation

[ ] Validate field mappings

[ ] Test error scenarios

[ ] Performance testing

[ ] Refine based on test results

Deliverables:

Test results document

Refined implementation

Performance benchmarks

Dependencies: Phase 2, Week 3

________________________________________________________________________________

### 4.3 Success Criteria

[ ] Can create change requests in ServiceNow

[ ] Can create incidents in ServiceNow

[ ] Field mappings are correct

[ ] Error handling works properly

[ ] Performance meets requirements

### 4.4 Testing

[ ] Unit tests for record creation

[ ] Integration tests with ServiceNow

[ ] Field mapping validation tests

[ ] Error scenario tests

________________________________________________________________________________

## 5. Phase 3: Tool Integrations

### 5.1 Objectives

Integrate each source tool (JIRA, GitHub, Ansible, OpenShift)

Configure webhooks for each tool

Implement tool-specific event processing

Test end-to-end flows

### 5.2 Tasks and Deliverables

#### Week 1-2: JIRA Integration

Tasks:

[ ] Configure JIRA webhooks

[ ] Set up JIRA authentication (OAuth/API tokens)

[ ] Implement JIRA event parsing

[ ] Create JIRA-to-ServiceNow mapping

[ ] Test JIRA webhook delivery

[ ] Implement JIRA event filtering

[ ] Create JIRA integration documentation

Deliverables:

JIRA webhook configuration

JIRA event processor

JIRA integration tested

JIRA integration documentation

Dependencies: Phase 2 completion

________________________________________________________________________________

#### Week 3-4: GitHub Integration

Tasks:

[ ] Configure GitHub webhooks

[ ] Implement HMAC signature verification

[ ] Create GitHub event parser

[ ] Implement GitHub-to-ServiceNow mapping

[ ] Handle GitHub rate limiting

[ ] Test GitHub webhook delivery

[ ] Create GitHub integration documentation

Deliverables:

GitHub webhook configuration

GitHub event processor

GitHub integration tested

GitHub integration documentation

Dependencies: Phase 2 completion

________________________________________________________________________________

#### Week 5-6: Ansible Integration

Tasks:

[ ] Configure Ansible webhooks

[ ] Set up Ansible API authentication

[ ] Implement Ansible event parsing

[ ] Create Ansible-to-ServiceNow mapping

[ ] Handle Ansible job status polling (fallback)

[ ] Test Ansible webhook delivery

[ ] Create Ansible integration documentation

Deliverables:

Ansible webhook configuration

Ansible event processor

Ansible integration tested

Ansible integration documentation

Dependencies: Phase 2 completion

________________________________________________________________________________

#### Week 7-8: OpenShift Integration

Tasks:

[ ] Configure Prometheus Alertmanager webhooks

[ ] Set up Kubernetes Watch API integration (optional)

[ ] Implement OpenShift event parsing

[ ] Create OpenShift-to-ServiceNow mapping

[ ] Handle high-volume event filtering

[ ] Test OpenShift webhook delivery

[ ] Create OpenShift integration documentation

Deliverables:

OpenShift webhook configuration

OpenShift event processor

OpenShift integration tested

OpenShift integration documentation

Dependencies: Phase 2 completion

________________________________________________________________________________

### 5.3 Success Criteria

[ ] All four tools integrated

[ ] Events from each tool create correct ServiceNow records

[ ] Tool-specific mappings work correctly

[ ] Webhook authentication verified

[ ] Integration documentation complete

### 5.4 Testing

[ ] End-to-end tests for each tool

[ ] Webhook delivery tests

[ ] Event parsing validation

[ ] Integration performance tests

________________________________________________________________________________

## 6. Phase 4: Resilience & Reliability

### 6.1 Objectives

Implement retry logic

Add ServiceNow outage handling

Implement queue persistence

Create health check mechanisms

### 6.2 Tasks and Deliverables

#### Week 1: Retry Logic Implementation

Tasks:

[ ] Implement exponential backoff retry strategy

[ ] Create retry configuration

[ ] Add retry tracking and logging

[ ] Implement max retry limits

[ ] Test retry scenarios

[ ] Create retry monitoring

Deliverables:

Retry logic implementation

Retry configuration

Retry monitoring dashboard

Retry testing results

Dependencies: Phase 2-3 completion

________________________________________________________________________________

#### Week 2: ServiceNow Outage Handling

Tasks:

[ ] Implement ServiceNow health check

[ ] Create outage detection logic

[ ] Implement queue accumulation during outages

[ ] Create recovery process

[ ] Implement backlog processing

[ ] Add outage alerting

[ ] Test outage scenarios

Deliverables:

Health check service

Outage handling logic

Recovery process

Outage testing results

Dependencies: Phase 4, Week 1

________________________________________________________________________________

#### Week 3: Queue Management Enhancement

Tasks:

[ ] Implement queue capacity monitoring

[ ] Create queue overflow handling

[ ] Implement priority-based processing

[ ] Add queue metrics and dashboards

[ ] Create queue management APIs

[ ] Test queue scenarios

Deliverables:

Enhanced queue management

Queue monitoring dashboards

Queue management APIs

Queue testing results

Dependencies: Phase 4, Week 1-2

________________________________________________________________________________

### 6.3 Success Criteria

[ ] Retry logic works correctly

[ ] ServiceNow outages are detected

[ ] Events are queued during outages

[ ] Recovery process works

[ ] Queue management operational

### 6.4 Testing

[ ] Retry logic tests

[ ] Outage simulation tests

[ ] Queue capacity tests

[ ] Recovery process tests

________________________________________________________________________________

## 7. Phase 5: Acknowledgment & Feedback

### 7.1 Objectives

Implement acknowledgment mechanism

Create acknowledgment handler

Update source systems with ServiceNow references

Implement bidirectional communication

### 7.2 Tasks and Deliverables

#### Week 1: Acknowledgment Mechanism

Tasks:

[ ] Extract ServiceNow record numbers from responses

[ ] Create acknowledgment payload structure

[ ] Implement acknowledgment storage

[ ] Create acknowledgment tracking

[ ] Test acknowledgment generation

Deliverables:

Acknowledgment mechanism

Acknowledgment payload schema

Acknowledgment tracking system

Dependencies: Phase 2-4 completion

________________________________________________________________________________

#### Week 2: Source System Updates

Tasks:

[ ] Implement JIRA update logic (comments, custom fields)

[ ] Implement GitHub update logic (comments, status checks)

[ ] Implement Ansible update logic (job notes, inventory)

[ ] Implement OpenShift update logic (annotations, events)

[ ] Test each source system update

[ ] Handle update failures gracefully

Deliverables:

JIRA update handler

GitHub update handler

Ansible update handler

OpenShift update handler

Update testing results

Dependencies: Phase 5, Week 1

________________________________________________________________________________

#### Week 3: End-to-End Acknowledgment Flow

Tasks:

[ ] Test complete acknowledgment flow for each tool

[ ] Validate ServiceNow references in source systems

[ ] Test acknowledgment failure scenarios

[ ] Implement acknowledgment retry logic

[ ] Create acknowledgment monitoring

[ ] Document acknowledgment process

Deliverables:

End-to-end acknowledgment tested

Acknowledgment monitoring dashboard

Acknowledgment documentation

Dependencies: Phase 5, Week 2

________________________________________________________________________________

### 7.3 Success Criteria

[ ] ServiceNow record numbers extracted correctly

[ ] Acknowledgments sent to all source systems

[ ] Source systems updated with ServiceNow references

[ ] Acknowledgment failures handled gracefully

[ ] Complete flow tested end-to-end

### 7.4 Testing

[ ] Acknowledgment generation tests

[ ] Source system update tests

[ ] End-to-end acknowledgment flow tests

[ ] Failure scenario tests

________________________________________________________________________________

## 8. Phase 6: Testing & Optimization

### 8.1 Objectives

Conduct comprehensive end-to-end testing

Performance tuning and optimization

Security testing

User acceptance testing

### 8.2 Tasks and Deliverables

#### Week 1: End-to-End Testing

Tasks:

[ ] Create comprehensive test scenarios

[ ] Test all event types from all tools

[ ] Test ServiceNow record creation for all scenarios

[ ] Test acknowledgment flows

[ ] Test outage and recovery scenarios

[ ] Test retry and error scenarios

[ ] Document test results

Deliverables:

Test scenarios document

Test execution results

Test report

Defect log

Dependencies: Phase 5 completion

________________________________________________________________________________

#### Week 2: Performance Testing

Tasks:

[ ] Load testing (high event volume)

[ ] Stress testing (peak load scenarios)

[ ] Latency testing (end-to-end processing time)

[ ] Queue capacity testing

[ ] ServiceNow API rate limit testing

[ ] Performance optimization

[ ] Performance benchmarks

Deliverables:

Performance test plan

Performance test results

Performance optimization report

Performance benchmarks

Dependencies: Phase 6, Week 1

________________________________________________________________________________

#### Week 3: Security Testing

Tasks:

[ ] Authentication and authorization testing

[ ] Webhook signature verification testing

[ ] Data encryption validation

[ ] Security vulnerability scanning

[ ] Penetration testing (if required)

[ ] Security compliance validation

[ ] Security test report

Deliverables:

Security test plan

Security test results

Vulnerability assessment

Security compliance report

Dependencies: Phase 6, Week 1-2

________________________________________________________________________________

#### Week 4: User Acceptance Testing

Tasks:

[ ] Prepare UAT environment

[ ] Create UAT test scenarios

[ ] Conduct UAT with business users

[ ] Gather UAT feedback

[ ] Address UAT findings

[ ] Obtain UAT sign-off

[ ] Document UAT results

Deliverables:

UAT test plan

UAT test scenarios

UAT results

UAT sign-off

Dependencies: Phase 6, Week 1-3

________________________________________________________________________________

### 8.3 Success Criteria

[ ] All test scenarios pass

[ ] Performance meets requirements

[ ] Security validated

[ ] UAT sign-off obtained

[ ] All critical defects resolved

________________________________________________________________________________

## 9. Phase 7: Production Deployment

### 9.1 Objectives

Deploy to production environment

Set up production monitoring

Conduct production validation

Provide training and documentation

### 9.2 Tasks and Deliverables

#### Week 1: Production Preparation

Tasks:

[ ] Prepare production infrastructure

[ ] Deploy production event management platform

[ ] Configure production ServiceNow integration

[ ] Set up production monitoring and alerting

[ ] Create production runbooks

[ ] Prepare rollback plan

[ ] Conduct pre-production checklist

Deliverables:

Production infrastructure ready

Production monitoring configured

Production runbooks

Rollback plan

Dependencies: Phase 6 completion

________________________________________________________________________________

#### Week 2: Phased Production Rollout

Tasks:

[ ] Deploy to production (Phase 1: JIRA only)

[ ] Monitor production metrics

[ ] Validate JIRA integration

[ ] Deploy Phase 2 (GitHub)

[ ] Validate GitHub integration

[ ] Deploy Phase 3 (Ansible)

[ ] Validate Ansible integration

[ ] Deploy Phase 4 (OpenShift)

[ ] Validate OpenShift integration

Deliverables:

Production deployment log

Production validation results

Production metrics dashboard

Dependencies: Phase 7, Week 1

________________________________________________________________________________

#### Week 3: Production Stabilization

Tasks:

[ ] Monitor production for issues

[ ] Address any production issues

[ ] Optimize based on production metrics

[ ] Fine-tune alerting thresholds

[ ] Conduct production health check

[ ] Create production support documentation

[ ] Handover to operations team

Deliverables:

Production support documentation

Operations runbook

Production health report

Operations handover document

Dependencies: Phase 7, Week 2

________________________________________________________________________________

### 9.3 Success Criteria

[ ] All integrations deployed to production

[ ] Production monitoring operational

[ ] No critical production issues

[ ] Operations team trained

[ ] Production documentation complete

________________________________________________________________________________

## 10. Resource Requirements

### 10.1 Team Structure

| Role | Allocation | Responsibilities |
| --- | --- | --- |
| Project Manager | 100% | Project coordination, stakeholder management |
| Solution Architect | 75% | Architecture design, technical decisions |
| ServiceNow Developer | 100% | ServiceNow integration, API development |
| Backend Developer | 100% | Event processing, integration development |
| DevOps Engineer | 75% | Infrastructure, deployment, monitoring |
| QA Engineer | 75% | Testing, test automation, quality assurance |
| Business Analyst | 50% | Requirements, UAT coordination |

### 10.2 Infrastructure Requirements

Development Environment:

Event management platform (Kafka/RabbitMQ)

Kubernetes cluster (development)

ServiceNow development instance

Monitoring and logging tools

Test Environment:

Event management platform (test)

Kubernetes cluster (test)

ServiceNow test instance

Test data and scenarios

Production Environment:

Event management platform (production, HA)

Kubernetes cluster (production, HA)

ServiceNow production instance

Production monitoring and alerting

________________________________________________________________________________

## 11. Risk Management

### 11.1 Risk Register

| Risk ID | Risk Description | Probability | Impact | Mitigation Strategy | Owner |
| --- | --- | --- | --- | --- | --- |
| R-001 | ServiceNow API changes | Medium | High | Version API calls, monitor ServiceNow updates | ServiceNow Developer |
| R-002 | High event volume | Medium | High | Load testing, auto-scaling, queue management | Backend Developer |
| R-003 | Tool API rate limits | High | Medium | Implement rate limiting, caching, batching | Backend Developer |
| R-004 | ServiceNow outages | Low | Critical | Queue management, retry logic, outage handling | Solution Architect |
| R-005 | Security vulnerabilities | Medium | High | Security testing, regular updates, monitoring | DevOps Engineer |
| R-006 | Integration complexity | High | Medium | Phased approach, proof of concept, testing | Solution Architect |
| R-007 | Resource availability | Medium | Medium | Early resource planning, backup resources | Project Manager |
| R-008 | Scope creep | Medium | Medium | Change control process, scope management | Project Manager |

________________________________________________________________________________

## 12. Success Metrics

### 12.1 Key Performance Indicators (KPIs)

| KPI | Target | Measurement |
| --- | --- | --- |
| Event Processing Latency (p95) | < 30 seconds | Average time from event ingestion to ServiceNow record creation |
| Event Processing Success Rate | > 99.5% | Percentage of events successfully processed |
| Acknowledgment Delivery Rate | > 99% | Percentage of acknowledgments successfully delivered |
| ServiceNow API Success Rate | > 99% | Percentage of successful ServiceNow API calls |
| Queue Processing Time | < 5 minutes | Average time events spend in queue |
| System Uptime | > 99.9% | Event processing system availability |
| Dead Letter Queue Rate | < 0.1% | Percentage of events in DLQ |

### 12.2 Business Metrics

| Metric | Target | Measurement |
| --- | --- | --- |
| Automated Ticket Creation | 80%+ | Percentage of tickets created automatically |
| Manual Ticket Reduction | 50%+ | Reduction in manual ticket creation |
| Time to Ticket Creation | < 1 minute | Time from event to ticket creation |
| User Satisfaction | > 4.0/5.0 | User satisfaction survey score |

________________________________________________________________________________

## 13. Dependencies and Assumptions

### 13.1 External Dependencies

ServiceNow instance access and API availability

Source tool access (JIRA, GitHub, Ansible, OpenShift)

Infrastructure provisioning and setup

Network connectivity between systems

Security approvals and access grants

### 13.2 Assumptions

ServiceNow API remains stable during project

Source tools support webhook functionality

Network connectivity is reliable

Sufficient infrastructure resources available

Team members available as planned

Requirements remain stable

________________________________________________________________________________

## 14. Communication Plan

### 14.1 Stakeholder Communication

| Stakeholder Group | Communication Frequency | Method |
| --- | --- | --- |
| Project Sponsor | Weekly | Status report, monthly meeting |
| Technical Team | Daily | Standup, Slack channel |
| Business Users | Bi-weekly | Demo sessions, updates |
| Operations Team | Weekly | Technical updates, handover prep |
| Management | Monthly | Executive summary, dashboard |

### 14.2 Reporting

**Daily:** Team standup, progress tracking

**Weekly:** Status report, risk register update

**Monthly:** Executive dashboard, milestone review

**Ad-hoc:** Issue escalation, change requests

________________________________________________________________________________

## 15. Change Management

### 15.1 Change Control Process

Change request submitted

Impact assessment conducted

Change review board evaluation

Approval/rejection decision

Implementation planning (if approved)

Change implementation

Change validation

Change closure

### 15.2 Scope Change Management

All scope changes require formal approval

Impact assessment (time, cost, resources)

Updated project plan and documentation

Stakeholder communication

________________________________________________________________________________

## Document Approval

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Project Sponsor | [Name] |  |  |
| Solution Architect | [Name] |  |  |
| Project Manager | [Name] |  |  |
| Technical Lead | [Name] |  |  |

________________________________________________________________________________

## Document History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | [Date] | [Name] | Initial roadmap |